## Simple Gantt Chart - EX
SIMPLE GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2023-03-12 | 2023-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2023-03-15 | 2023-03-16 | 1 | 100%
1.2 | Research | Pete S | 2023-03-15 | 2023-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2023-03-16 | 2023-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2023-03-17 | 2023-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2023-03-18 | 2023-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2023-03-23 | 2023-03-23 |  | 50%
2 | Project Definition and Planning
2.1 | Scope and Goal Setting | Steve L | 2023-03-24 | 2023-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2023-03-29 | 2023-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  |  | 0%
2.4 | Risk Management | Malik M |  |  |  | 0%
3 | Project Launch and Execution
3.1 | Status and Tracking | Pete S |  |  |  | 0%
3.2 | KPIs | Leon W |  |  |  | 0%
3.2.1 | Monitoring | Kylie R |  |  |  | 0%
3.2.2 | Forecasts | Kylie R |  |  |  | 0%
3.3 | Project Updates | Pete S |  |  |  | 0%
3.3.1 | Chart Updates | Malik M |  |  |  | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0%
4.2 | Quality Deliverables | Allen W |  |  |  | 0%
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0%
4.4 | Project Performance | Malik M |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## Simple Gantt Chart - BLANK
ProTech Gantt Chart
PROJECT TITLE | ProTech
PROJECT MANAGERS | Camila, Clinton, Kaiya, & Shayne
START DATE | 2023-05-16
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Developer 1 (Back-End) | Shayne
1.1 | Server Setup |  | 2023-05-25 | 2023-05-30 | 5 | 100%
1.1.1 | DataBase Connection |  | 2023-05-25 | 2023-06-01 | 7 | 100%
1.2 | API Endpoints |  | 2023-05-25 | 2023-06-06 | 12 | 100%
1.3 | Define an API route that handles search requests and captures the search query parameters (name or category) |  | 2023-05-31 | 2023-06-10 | 10 | 100%
1.4 | Utilize database queries (MySQL) to search for products that match the specified name or category |  | 2023-05-31 | 2023-06-17 | 17 | 90%
1.5 | Retrieve the search results from the database and send them as a response to the client-side search requests |  | 2023-05-31 | 2023-06-23 | 23 | 95%
1.6 | Implement user registration/authentication and login |  | 2023-06-13 | 2023-06-25 | 12 | 80%
1.7 | Produce and successfully connect php files to fetch and search products logged in the database |  | 2023-06-13 | 2023-07-05 | 22 | 65%
2 | Developer 2 (Back-End) | Clinton
2.1 | User Reviews to be implemented into API endpoints |  | 2023-05-25 | 2023-06-02 | 8 | 100%
2.2 | Routes to create new reviews |  | 2023-05-25 | 2023-06-11 | 17 | 100%
2.3 | Have functionality connected to the database |  | 2023-05-25 | 2023-06-25 | 31 | 100%
2.4 | Define API routes and corresponding functions to handle submitting new reviews and retrieving reviews for a specific product |  | 2023-05-31 | 2023-06-12 | 12 | 90%
2.5 | Implement database operations (insertion and retrieval) to store and retrieve review data from the MySQL database |  | 2023-05-31 | 2023-06-17 | 17 | 85%
2.6 | Ensure proper data validation and handling of user reviews to maintain data integrity |  | 2023-05-31 | 2023-06-24 | 24 | 80%
2.7 | Implement search functionality to allow users to search for a product listed on the ProTech products page from a search Bar |  | 2023-06-13 | 2023-06-26 | 15 | 90%
3 | Developer 1 (Front-End) | Camila
3.1 | Work on the product listing page(home page) |  | 2023-05-24 | 2023-05-31 | 7 | 100%
3.2 | Design and implement the individual Home/product page using HTML and CSS |  | 2023-05-31 | 2023-06-25 | 25 | 85%
3.2.1 | Display detailed information about a specific product, including images, descriptions, specifications, and user reviews |  | 2023-05-31 | 2023-06-15 | 15 | 100%
3.2.2 | Support Shayne with the database setup |  | 2023-05-31 | 2023-06-08 | 8 | 100%
3.3 | Develop the product listing and details pages |  | 2023-06-13 | 2023-06-23 | 10 | 100%
3.3.1 | Set up the necessary links or buttons that direct users to the respective Amazon product pages for purchasing |  | 2023-06-13 | 2023-06-29 | 16 | 95%
4 | Developer 2 (Front-End) | Kaiya
4.1 | Design and implement the user reviews section |  | 2023-05-27 | 2023-06-01 | 5 | 90%
4.2 | Enhance navigation and user interactivity using JavaScript |  | 2023-05-31 | 2023-06-17 | 17 | 75%
4.3 | Add functionality to navigation menus and implement user interactions such as adding products to a wishlist or submitting a review |  | 2023-05-31 | 2023-06-26 | 26 | 90%
4.4 | Add product search functionality |  | 2023-06-13 | 2023-06-28 | 15 | 80%
4.5 | Incorporate user reviews and ratings |  | 2023-06-13 | 2023-06-30 | 17 | 70%

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.